Project Conclusions

- The success of the  Barcelona Project must be seen as the success of an

Irish Government initiative leading towards the creation of an inclusive society.

In this context the Barcelona Declaration has proven to be the right tool to focus on Disability issues and to address them directly at  local community level.

- European initiatives such as the Barcelona Declaration, should be conceived

in operational terms as well as inspirational terms to fully benefit society.

The “What” is as important as the “How”. The Barcelona Project in Ireland constitutes the “How”

- The positive impact of the Barcelona Declaration in Ireland is due to

consolidated approach 	involving the National Disability Authority, County/City Development Boards, Local Authorities, Institute for Design and Disability (whose team has delivered the Project), people with disabilities and their advocates.

- The Project reached its objectives as stated in the Terms of Reference:

- promoted the Barcelona Declaration and  	identified it with the Equality legislation in 	Ireland,

- exceeded the required 75% of adoptions,

- achieved  82%, the highest rate of adoption 	in Europe,

developed Disability proof decision-	making process,

- produced Disability Proofing Template,

- condensed the 17 Agreements into 6 	readily recognisable essential objectives,

- identified the Consultative process as 	the most important element of the 	Declaration.

- ensured that ownership of models of 	good practice is identified with the local 	authority personnel who developed them .

- The Terms of reference of the Project focused on local authorities. The Project Team concentrated on delivering a programme, which enabled local authorities to disability-proof their decision-making process. There is a need to develop a corresponding programme for disabled people in order to make the consultative process more effective and meaningful.

- To date, most local authorities are at the transition stage between the act of adoption and the act of planning the implementation. Learning from the European experience, “follow-up” support is required to ensure the sustainability of the implementation and to disseminate models of good practice.

- The Disability proofing process has only just been introduced. The Impact

Assessment has not been fully tested. The local authorities, which lead  the implementation and those at the transition stage would benefit from

having their work proactively monitored after the completion of this Project.

- “Ireland took the Declaration as a national policy and gained from it.

Ireland is now heading the European Union’s Council of Ministers…who better to build on the Barcelona Declaration in a new ‘Celtic Strategy’ for a fairer, better Europe?”

(Pete Kercher, President, European Institute for Design and Disability)